## Product Backlog
Product Name: | Chill
Name: | Said Adem
Initials: | SA
Student ID: | 1000873053
Total Features | Left | Available | Completed | Sprint Ends
Start | 32 | 0 | 0
Sprint 1 | 22 | 10 | 10 | 2018-03-30
Sprint 2 | 14 | 18 | 18 | 2018-04-08
Sprint 3 | 10 | 22 | 22 | 2018-04-15
Sprint 4 | 9 | 23 | 23 | 2018-04-22
Sprint 5 | 0 | 32 | 32 | 2018-04-29
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Priority | Status | Expected Sprint | Actual Sprint # | As a … | I want to… | So that… | Type | Notes
CM | 1 | CMP | 1 | 1 | PM | Create any type of media | I can check out media and create bundles | CLI | No Menu Required
BN | 2 | CMP | 1 | 1 | PM | Create a bundle of media | I can check out bundles | CLI | No Menu Required
| 3 | CMP | 1 | 1 | PM | Create a Librarian | They can check out/in media | CLI | No Menu Required
| 4 | CMP | 1 | 1 | LB | Create a Customer | We can keep track of who has what media | CLI | No Menu Required
| 5 | CMP | 2 | 2 | CU | Browse Catalog | they can see what is available | CLI | Need to list all media. Also list all bundles and media in those bundles. Creating Menu
| 6 | CMP | 2 | 2 | PM | Add or Create | I can do it from a menu | CLI | Requires MVC
| 7 | CMP | 2 | 2 | LB | Check out Media | Customers can check out books | CLI | Librarian creates transaction with customer info
| 8 | CMP | 2 | 2 | LB | Check in Media | Customers can check in books | CLI | Librarian modifies transaction to check in
| 9 | CMP | 2 | 2 | CU | Pay Balance | Pay fine and check out new books | CLI | Customer can't check out media till balance is paid
| 10 | CMP | 2 | 2 | PM | Save/Load Data | Don’t loose records of clients, media, and transaction | CLI | Should be options in the menu
| 11 | CMP | 3 | 3 | ALL | Open a main GUI Window | I can use my mouse | GUI | Just opening a window
| 12 | CMP | 3 | 3 | PM | Create Media and Bundles Via GUI | Make this process more user friendly | GUI | Be able to do this in dialog windows
| 13 | CMP | 3 | 3 | CU | Browse GUI Catalog | They can see what is available | GUI | Dialog Windows
| 14 | NS | 4 | 5 | PM | Create Librarians via GUI | They can check out/in media | GUI | Same as before but in a GUI
| 15 | NS | 4 | 5 | LB | Create Customers via aGUI | We can keep track of who has what media | GUI | Same as before but in a GUI
| 16 | NS | 4 | 5 | LB | Check out Media in GUI | Customers can check out books | GUI | Same as before but in a GUI
| 17 | NS | 4 | 5 | LB | Check in Media in GUI | Customers can check in books | GUI | Same as before but in a GUI
| 18 | NS | 4 | 5 | CU | Pay Balance in GUI | Pay fine and check out new books | GUI | Same as before but in a GUI
| 19 | NS | 4 | 5 | ALL | See a menu Bar | Make it easier to find stuff | GUI | Still have dialog boxes, but main menu dialog box is replaced with menu bar
| 20 | NS | 5 | 5 | PM | See everything that’s checked out and to who | See what's not in the library | GUI | A scrollable list
| 21 | NS | 5 | 5 | PM | Save/Load Data to default file name | Don’t loose records of clients, media, and transaction | GUI | Save to whatever file was opened, or a defualt name
| 22 | NS | 5 | 5 | PM | Save and Load from different file names | Manage multiple libraries | GUI | Save/load to a user specified file
| 23 | NS | 6 |  | CU | See pictures of the media | So customers can see what book to look for | GUI | Picture must be added when creating media
| 24 | NS | 6 |  | ALL | Have users log in | So not all options are available to everyone | GUI | Can be hardcoded user names and passwords, such as "PM" for project manager with password "password". Each user type must have different usernames and passwords
| 25 | NS | 6 |  | LB | Bulk Check Out/In | So that librarians can check out multiple books at once | GUI | One window where multiple media ids can be typed, and check out multiple customers at once
| 26 | NS | 7 |  | ALL | Undo | Undo mistakes | GUI | Undo events (add media, check out, etc)
| 27 | NS | 7 |  | ALL | Copy Paste | Not waste time typing | GUI | Just do it where you can. It's built in some places. Don't start your own.
| 28 | NS | 7 |  | ALL | Have this in one window | It's not full of pop up dialog boxes | GUI | All contents in a window. Different window layout for different users

## Sprint 1
Sprint # | 1
Start on | 2018-03-24
End on | 2018-03-30
Total Tasks | 10
Day 1 Left | 10
Day 2 Left | 10
Day 3 Left | 10
Day 4 Left | 10
Day 5 Left | 7
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CM | Architecture | UML | SA | Add methods to Media and derived classes | Completed
2 | CM | Media | Code | SA | Write and compile empty Media class | Completed
3 | CM | Media | Code | SA | Variables and Constructor | Completed
4 | CM | Media | Code | SA | Operator Overload << | Completed
5 | CM | Media | Test | SA | Test Constructor and << | Completed
6 | CM | Media | Code | SA | Add Get Methods | Completed
7 | CM | Media | Test | SA | Test get methods in main | Completed
8
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Wrap Up | UML | Initials Here | Update UML to match new methods if changed | Completed
N + 1 | BN | Architecture | UML | Initials Here | Add methods to Bundle and derived classes | Completed
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Wrap_Up | Delivery | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | Completed

## Sprint 2
Sprint # | 2
Start on | 2018-04-02
End on | 2018-04-08
Total Tasks | 8
Day 1 Left | 8
Day 2 Left | 8
Day 3 Left | 5
Day 4 Left | 5
Day 5 Left | 5
Day 6 Left | 2
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | PM | Architecture | UML | SA | Update UML | Completed
2 | CU | Media | Code | SA | Browse Catalog | Completed
3 | PM | Media | Code | SA | Add or Create | Completed
4 | LB | Media | Code | SA | Check out Media | Completed
5 | LB | Media | Code | SA | Check in Media | Completed
6 | CU | Media | Code | SA | Pay Balance | Completed
7 | PM | Media | Code | SA | Save/Load | Completed | Ommitted by Gieser
8 | PM | Media | Test | SA | Test menu options | Completed

## Sprint 3
Sprint # | 3
Start on | 2018-04-09
End on | 2018-04-15
Total Tasks | 4
Day 1 Left | 4
Day 2 Left | 4
Day 3 Left | 4
Day 4 Left | 3
Day 5 Left | 3
Day 6 Left | 3
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | ALL | GUI | Code | SA | Open a main GUI Window | Completed
2 | PM | GUI | Code | SA | Create Media and Bundles Via GUI | Completed
3 | CU | GUI | Code | SA | Browse GUI Catalog | Completed
4 | PM | Architecture | UML | SA | Update UML | Completed

## Sprint 4
Sprint # | 4
Start on | 2018-04-16
End on | 2018-04-22
Total Tasks | 7
Day 1 Left | 7
Day 2 Left | 7
Day 3 Left | 7
Day 4 Left | 7
Day 5 Left | 7
Day 6 Left | 7
Day 7 Left | 6
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | PM | GUI | Code | SA | Create Librarians via GUI | NC | 3 tests this week. Will be done with sprint 5.
2 | LB | GUI | Code | SA | Create Customers via aGUI | NC | 3 tests this week. Will be done with sprint 5.
3 | LB | GUI | Code | SA | Check out Media in GUI | NC | 3 tests this week. Will be done with sprint 5.
4 | LB | GUI | Code | SA | Check in Media in GUI | NC | 3 tests this week. Will be done with sprint 5.
5 | CU | GUI | Code | SA | Pay Balance in GUI | NC | 3 tests this week. Will be done with sprint 5.
6 | ALL | GUI | Code | SA | See a menu Bar | NC | 3 tests this week. Will be done with sprint 5.
7 | PM | Architecture | UML | SA | Update UML | Completed

## Sprint 5
Sprint # | 5
Start on | 2018-04-23
End on | 2018-04-29
Total Tasks | 12
Day 1 Left | 12
Day 2 Left | 12
Day 3 Left | 12
Day 4 Left | 12
Day 5 Left | 5
Day 6 Left | 3
Day 7 Left | 3
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | PM | Media | GUI | SA | Create Media and Bundles Via GUI | CMP
2 | PM | Media | GUI | SA | Create Librarians via GUI | CMP
3 | LB | Media | GUI | SA | Create Customers via aGUI | CMP
4 | LB | Media | GUI | SA | Check out Media in GUI | CMP | Done through cli. It's a feature…
5 | LB | Media | GUI | SA | Check in Media in GUI | CMP | Done through cli. It's a feature…
6 | CU | Media | GUI | SA | Pay Balance in GUI | CMP
7 | ALL | Media | GUI | SA | See a menu Bar | NC | I didn't know how to implement it
8 | PM | Media | GUI | SA | See everything that’s checked out and to who | CMP
9 | PM | File | GUI | SA | Save/Load Data to default file name | NC | Could not complete this task in time
10 | PM | File | GUI | SA | Save and Load from different file names | NC | Could not complete this task in time
11 | PM | UML | Architecture |  | Update UML diagram | CMP
12 | PM | UML | Architecture |  | Create Use Case Diagram | CMP